## Schedule
| CMER Master Project Schedule | [47 empty] | All critical projects are to be completed by 2031 by WAC | [14 empty] | HCP over
| Recommended FP HCP Adaptive Management Program Priority Projects |  | Assumed Annual Cost
| 7/29/14 - Draft |  | 75000 | 150000 | 350000 | 150000 | 75000
| Project | Project Priority | Years by Study Phase | [6 empty] | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 |  |  | Completion |  |  | Settlement Agreement | Project Priority | Recommend Action | Budget | YTD | Actual
|  |  | St Design | Site Selection | Implementation | Anal & Rpt Writing | Review & Approval | Total years | Total Cost | STD1 | STD2 | SS1 | IMPL1 | IMPL2 | IMPL3 | IMPL4 | IMPL5 | IMPL6 | A&W1 | A&W2 | RA&1 | R&A2 | TOTAL |  | Date | 2013 | 2014 |  |  |  | 2015 | 2015 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052
Administrative and Support Staff
| CMER Science Staff | [24 empty] | 560000 | 560000 |  |  |  | 601000 |  |  | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000
| Project Support | [24 empty] | 337000 | 437000 |  |  |  | 487000 |  |  | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000
| Project Administration | [24 empty] | 312000 | 267000 |  |  |  | 267000 |  |  | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000
Projects almost finished
8 | Buffer Integrity - Shade effectiveness (amphibian response) | 1 | [21 empty] | 81001 | CWA 2012 | 25000 | 26000 | Yes | 1 | retain | Budget 2015: 30000
#REF! | Forest Practices and Wetlands Systematic Literature Review | 1 | [6 empty] | 50000 | [14 empty] | 167001 | CWA 2012 | 50000 | 57000 | Yes | 1 | retain | Budget 2015: 60000
#REF! | Wetlands Program Research Strategy | 2 | [22 empty] | CWA 2013 |  | 50000 | Yes | 2 | retain | Budget 2015: 33000
#REF! | Type F and N Extensive Westside - Temperature (Baseline status) | 1 |  |  |  |  | 1 | 1 | 75000 | [12 empty] | 75000 |  | 32501 | CWA 2015 | 7500 | 15000 | Yes | 1 | retain | Budget 2015: 10000
6 | Eastside Type N Forest Hydrology | 1 | [6 empty] | 450000 | [14 empty] | 965001 |  | 350000 | 190000 | Yes | 1 | retain | Budget 2015: 425000
| RMZ birds | [26 empty] | No |  | retain | Budget 2015: 2000
#REF! | Eastern Washington Riparian Assessment (EWRAP) | 1 | [21 empty] | 150001 |  | 50000 | 50000 | Yes | 1 | revisit | Actual 2016: 50000
#REF! | Riparian Hardwood Conversion | 1 | [21 empty] | 95001 |  | 2000 | 10000 | Yes | 1 | revisit | Budget 2015: 10000; Actual 2016: 73000
Projects on the ground and far along
1 | Type N Experimental Buffer Treatment Project in Hard Rock Lithologies | 1 | [21 empty] | 1034001 | CWA 2014 | 237000 | 179000 | Yes | 1 | retain | Budget 2015: 304000; Actual 2016: 214000; Actual 2017: 100000
2 | Type N Experimental Buffer Treatment Project - Hard Rock- Amphibian Genetics - Post sample | 1 | [25 empty] | Yes | 1 | retain | Budget 2015: 0; Actual 2016: 200000; Actual 2017: 200000; Actual 2018: 85000; Actual 2019: 40000
3 | Type N Experimental Buffer Treatment Project - Hard Rock- Amphibian Demographics/Channel Metrics | [7 empty] | 940000 | [14 empty] | 802000 | CWA NA |  | 25000 | No |  | retain | Budget 2015: 0; Actual 2016: 165000; Actual 2017: 231000; Actual 2018: 153000; Actual 2019: 153000; Actual 2020: 75000
4 | Type N Experimental Buffer Treatment Project in Hard Rock Lithologies - Temp/Sediment/Vegetation/Litterfall | [25 empty] | 163000 | No |  | retain | Budget 2015: 134000; Actual 2016: 320000; Actual 2017: 190000; Actual 2018: 119000; Actual 2019: 0
5 | Type N Experimental Buffer Treatment Project - Soft Rock Lithologies | 1 | [21 empty] | 2256001 | CWA 2018 | 360000 | 360000 | Yes | 1 | retain | Budget 2015: 344000; Actual 2016: 382000; Actual 2017: 360000; Actual 2018: 216000; Actual 2019: 153000; Actual 2020: 81000
Other Projects
7 | Eastside Type N Riparian Effectiveness - Perennial | 1 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2695001 | CWA 2019 | 75000 | 75000 | Yes | 1 | revisit | Budget 2015: 5000; Actual 2016: 100000; Actual 2017: 250000; Actual 2018: 360000; Actual 2019: 360000; Actual 2020: 360000; Actual 2021: 360000; Actual 2022: 360000; Actual 2023: 250000; Actual 2024: 100000; Actual 2025: 40000
| Eastside Type N Riparian Effectiveness - Dry | [26 empty] | Yes | ? | revisit | Budget 2015: 80000; Actual 2016: 75000; Actual 2017: 150000; Actual 2018: 330000; Actual 2019: 330000; Actual 2020: 330000; Actual 2021: 330000; Actual 2022: 330000; Actual 2023: 200000; Actual 2024: 100000; Actual 2025: 40000
#REF! | Unstable Slopes Criteria Evaluation and Development | 1 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 |  | 875001 | CWA Scope 2013 | 50000 | 50000 | Yes | 1 | retain | Budget 2015: 150000; Actual 2016: 150000; Actual 2017: 150000; Actual 2018: 150000; Actual 2019: 100000; Actual 2020: 75000
| Glacial Deep Seated - Develop or implement Strategy | [26 empty] | No |  | retain | Budget 2015: 50000
[40 empty] | 10000 | 150000 | 150000 | 150000 | 150000 | 100000 | 75000
#REF! | Forested Wetlands Effectiveness Study | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2565000 | CWA Scope 2013 | 75000 | 75000 | Yes | 2 | retain | Budget 2015: 25000; Actual 2016: 100000; Actual 2017: 250000; Actual 2018: 360000; Actual 2019: 360000; Actual 2020: 360000; Actual 2021: 360000; Actual 2022: 360000; Actual 2023: 250000; Actual 2024: 100000; Actual 2025: 40000
#REF! | Wetland/Stream Water Temp Interactions (Subquestion) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | Actual 2016: 50000; Actual 2017: 50000; Actual 2018: 50000; Actual 2019: 50000; Actual 2020: 50000; Actual 2021: 50000; Actual 2022: 50000; Actual 2023: 50000; Actual 2024: 50000; Actual 2025: 25000
#REF! | Wetland Hydrologic Connectivity (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | Actual 2016: 50000; Actual 2017: 50000; Actual 2018: 50000; Actual 2019: 50000; Actual 2020: 50000; Actual 2021: 50000; Actual 2022: 50000; Actual 2023: 50000; Actual 2024: 50000; Actual 2025: 25000
#REF! | Wetlands Management Zone Effectiveness Monitoring | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2565002 |  |  |  | Yes | 2 | retain | Actual 2023: 25000; Actual 2024: 100000; Actual 2025: 250000; Actual 2026: 360000; Actual 2027: 360000; Actual 2028: 360000; Actual 2029: 360000; Actual 2030: 360000; Actual 2031: 250000; Actual 2032: 100000; Actual 2033: 40000
#REF! | Wetland/Stream Water Temp Interactions (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | Actual 2024: 50000; Actual 2025: 50000; Actual 2026: 50000; Actual 2027: 50000; Actual 2028: 50000; Actual 2029: 50000; Actual 2030: 50000; Actual 2031: 50000; Actual 2032: 50000; Actual 2033: 25000
#REF! | Wetland Hydrologic Connectivity (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | Actual 2024: 50000; Actual 2025: 50000; Actual 2026: 50000; Actual 2027: 50000; Actual 2028: 50000; Actual 2029: 50000; Actual 2030: 50000; Actual 2031: 50000; Actual 2032: 50000; Actual 2033: 25000
#REF! | Westside Type F Riparian Prescription Monitoring | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2625002 | CWA Scope 2014 |  | 75000 | Yes | 2 | retain | Budget 2015: 10000; Actual 2016: 100000; Actual 2017: 250000; Actual 2018: 360000; Actual 2019: 360000; Actual 2020: 360000; Actual 2021: 360000; Actual 2022: 360000; Actual 2023: 250000; Actual 2024: 100000; Actual 2025: 40000
#REF! | Road Prescription-Scale Effectiveness Monitoring | 2 | 1 | 1 | 6 | 2 | 2 | 12 | 2775000 | 75000 |  | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2775000 | 40000 | CWA Scope 2013 |  | 75000 | Yes | 2 | retain | Budget 2015: 25000; Actual 2016: 100000; Actual 2017: 250000; Actual 2018: 360000; Actual 2019: 360000; Actual 2020: 360000; Actual 2021: 360000; Actual 2022: 360000; Actual 2023: 250000; Actual 2024: 100000; Actual 2025: 40000
#REF! | Road Sub-Basin-Scale Effectiveness Monitoring - Resample | 1 | 1 | 1 | 1 | 1 | 2 | 6 | 900000 |  |  | 150000 | 350000 | 350000 |  |  |  |  | 150000 |  | 75000 | 75000 |  | 1000001 | CWA 2018 |  |  | Yes | 1 | Revisit | Actual 2023: 75000; Actual 2024: 350000; Actual 2025: 350000; Actual 2026: 150000; Actual 2027: 75000
#REF! | Watershed Scale Assessment of Cumulative Effects (sed and temp) (roads and riparian) | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2580002 | CWA Scope 2016 |  |  | Yes | 2 | retain | Actual 2026: 40000; Actual 2027: 100000; Actual 2028: 250000; Actual 2029: 360000; Actual 2030: 360000; Actual 2031: 360000; Actual 2032: 360000; Actual 2033: 360000; Actual 2034: 250000; Actual 2035: 100000; Actual 2036: 40000
#REF! | Amphibians in Intermittent Streams | 2 | 1 | 1 | 3 | 1 | 2 | 8 | 1575000 | [14 empty] | 2630002 | CWA Scope 2016 |  |  | Yes | 2 | retain (d) | Actual 2019: 40000; Actual 2020: 150000; Actual 2021: 250000; Actual 2022: 360000; Actual 2023: 360000; Actual 2024: 360000; Actual 2025: 360000; Actual 2026: 360000; Actual 2027: 250000; Actual 2028: 100000; Actual 2029: 40000
#REF! | Wetlands Intensive Monitoring | 6 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 | 1800000 | 1830000 |  |  |  | Yes | 6 | retain (c) | Actual 2031: 40000; Actual 2032: 100000; Actual 2033: 250000; Actual 2034: 360000; Actual 2035: 360000; Actual 2036: 360000; Actual 2037: 360000; Actual 2038: 360000; Actual 2039: 250000; Actual 2040: 100000; Actual 2041: 40000
#REF! | Type F Experimental Buffer Treatment (maybe use to address gaps any unaswered F questions) | 3 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2580000 |  |  |  | Yes | Unspecified | revisit | Actual 2025: 40000; Actual 2026: 100000; Actual 2027: 250000; Actual 2028: 360000; Actual 2029: 360000; Actual 2030: 360000; Actual 2031: 360000; Actual 2032: 360000; Actual 2033: 250000; Actual 2034: 100000; Actual 2035: 40000
#REF! | Pathways of Riparian Stand Development to Maturity (Westside) | 4 | 1 | 1 | 2 | 1 | 2 | 7 | 1225000 | 75000 |  | 150000 | 150000 | 150000 |  |  |  |  | 150000 |  | 75000 | 75000 | 825000 | 785000 |  |  |  | Yes | 4 | revisit | Actual 2025: 10000; Actual 2026: 150000; Actual 2027: 150000; Actual 2028: 150000; Actual 2029: 150000; Actual 2030: 100000; Actual 2031: 75000
#REF! | Type F Performance Target Validation (Westside) | 6 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 | 1800000 | 785000 |  |  |  | Yes | 6 | revisit | Actual 2027: 10000; Actual 2028: 150000; Actual 2029: 150000; Actual 2030: 150000; Actual 2031: 150000; Actual 2032: 100000; Actual 2033: 75000
| Van Dykes Salamander Project | [26 empty] | Yes | Unspecified | revisit | Budget 2015: 56000; Actual 2019: 284000; Actual 2020: 103000; Actual 2021: 266000; Actual 2022: 103000
| Windthrow Data Synthesis | [29 empty] | Actual 2026: 50000
| GDSL Placeholder | [29 empty] | Actual 2016: 100000; Actual 2017: 100000; Actual 2018: 100000
| Extensive Alternative | [29 empty] | Actual 2016: 100000; Actual 2017: 100000; Actual 2018: 100000; Actual 2019: 100000; Actual 2029: 300000
[24 empty] | TOTAL |  | 2535500 | 2875000 |  |  |  | 3108000 |  |  | 3584000 | 3936000 | 4048000 | 3995000 | 3609000 | 3641000 | 3598000 | 3165000 | 2915000 | 2765000 | 2715000 | 2650000 | 2800000 | 3075000 | 2685000 | 2590000 | 2375000 | 2280000 | 1965000 | 1755000 | 1655000 | 1615000 | 1615000 | 1505000 | 1355000 | 1295000 | 1255000 | 1255000 | 1255000 | 1255000 | 1255000 | [5 empty] | 0
| (difference from $4 million) | [29 empty] | 892000 |  |  | 416000 | 64000 | -48000 | 5000 | 391000 | 359000 | 402000 | 835000 | 1085000 | 1235000 | 1285000 | 1350000 | 1200000 | 925000 | 1315000 | 1410000 | 1625000 | 1720000 | 2035000 | 2245000 | 2345000 | 2385000 | 2385000 | 2495000 | 2645000 | 2705000 | 2745000 | 2745000 | 2745000 | 2745000 | 2745000
#REF! | Fish Passage Effectiveness Monitoring | [29 empty] | Actual 2016: 130000; Actual 2017: 130000; Actual 2020: 130000; Actual 2025: 130000; Actual 2035: 130000
| Extensive Fish Passage Trend Monitoring | [26 empty] | Alternate List | DNR task? | Revist, before Board | Budget 2015: 0
Landslide Projects TBD
| Landslide Classification (deep seated landslides) | [26 empty] | Alternate List |  | Revisit after subgroup | Actual 2016: 100000
| Groundwater Recharge Modeling and Model Refinement | [26 empty] | Alternate List |  | Revisit after subgroup | Actual 2016: 60000
| Evapo-Transpiration Model Refinement | [26 empty] | Alternate List |  | Revisit after subgroup | Actual 2017: 60000
| Mass Wasting Validation Program (Intensive) | [26 empty] | Alternate List |  | Hold pending mass wasting strategy | Actual 2017: 40000; Actual 2018: 100000; Actual 2019: 250000; Actual 2020: 360000; Actual 2021: 360000; Actual 2022: 360000; Actual 2023: 360000; Actual 2024: 360000; Actual 2025: 250000; Actual 2026: 100000; Actual 2027: 40000
| Mass Wasting Landscape-Scale Effectiveness Monitoring | 2 | 2 | 1 | 4 | 2 | 2 | 11 | 2150000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 |  |  | 150000 | 150000 | 75000 | 75000 | 2150000 | 785000 | CWA Scope 2010 |  |  | Yes | 2 | revisit | Actual 2016: 80000
| Revise Shallow Rapid Lanslide Screen (westside) using LiDAR | [26 empty] | No |  | Hold pending MW Strategy discussion | Actual 2016: 10000; Actual 2017: 150000; Actual 2018: 150000; Actual 2019: 150000; Actual 2020: 150000; Actual 2021: 100000; Actual 2022: 75000
[24 empty] | TOTAL |  | 1281500 | 1500000 |  |  |  | 3108000 |  |  | 3964000 | 4316000 | 4298000 | 4395000 | 4249000 | 4101000 | 4033000 | 3525000 | 3275000 | 3145000 | 2815000 | 2690000 | 2800000 | 3075000 | 2685000 | 2590000 | 2375000 | 2280000 | 1965000 | 1885000 | 1655000 | 1615000 | 1615000 | 1505000 | 1355000 | 1295000 | 1255000 | 1255000 | 1255000 | 1255000 | 1255000
Note on AA48: Hicks, Mark (ECY): Ecology supports 2021 date and may drop this milestone if RMAP program improvements prove sufficient.
Note on AG8: ceh: FY15: includes $100,000 for LiDAR water typing model pilots
Note on AL26: Mark Hicks: Based on consultation with Bill E I dropped FY18 and 19 by 40% assuming harvets occur as per agreement with landowners. This was a change from 360K 2018 and 255K in 2019.
Note on AJ18: Mark Hicks: This may end up not being requested and can be done anytime using the final data.
Note on AJ19: Mark Hicks: Policy needs to determine if this 10-year free to grow data is desirable.
Note on AG30: Mark Hicks: For TWIG to have outside entity as coordinator on field data collection with the other consultants, and to keep on retainer to begin help TWIG as a lead writer developing study desgin once data is collected.
Note on AJ22: Mark Hicks: Final cost heavily depends on the nature of the review comments received, but will probably be less than budgeted if reanalysis and major re-write is not needed.
Note on AM51: Mark Hicks: Project moved out two years since need for study will not be determined until hard rock amphibian analyses are complete. Is there reason to assume it will be 100K to develop a study design?
Note on AT50: Moved out to after W. F Effectiveness study is complete so that knowledge plus what is learned from the Type N studies can go into developing a study design
Note on AG57: mhic461: Phase I start of three phase project. Can break up timing of different phases. Originally this was 56K, 237K, 103K, 266K, and 103K. Currently the second year of phase one includes costs for first year of phase 2.
Note on B55: mhic461: Is this a priority? The purpose of this project is to determine the development sequence of younger stands of various species compositions and densities to mature stands. The study is intended to inform management of uneven-aged stands and those of low density or mixed composition.
Note on AQ48: mhic461: Moved from 2021 to manage budget bump.
Note on AR48: mhic461: I broke a 700K field season into two years of 350K each.
Note on B56: mhic461: This project will evaluate the validity of the Type F performance targets and the measures of success in meeting resource objectives. Will this really be a stand alone project or will we use the efectiveness study results to make recommendations?
Note on B65: mhic461: Will operational checks on fish passage as part of RMAP program suffice to provide status of fish passage on regional scale and how conditions are changing over time?
Note on AG29: mhic461: Greg suggests allocating money to begin finding sites in 2015. But this part of budget was approved and going to Boartd.
Note on B39: mhic461: Anticipated to major experimental studies with temp and connectivity as add-on costs.
Note on AN26: mhic461: This represents a 5th year post resample of vegetation to sync up with West BCIF data.
Note on AL30: mhic461: Field monitoring cost estimates dropped from 360K/yr to 330K/yr anticipating some savings if done concurrently with perennial flow study.
Note on AQ30: mhic461: Analysis costs lowered from 250K to 200K expecting some savings due to staff efficiency if done concurrent with perennial flow study.
Note on AN51: mhic461: Default costs raised from 100K for first year of site acquisition to 150k in recognition of greater logistical challenges in finding amphibian study sites.
Note on AM25: mhic461: Dropped the 75K that was in 2019 given policy has provided the ability for this extended montioring to be completed without going through ISPR.
Note on B71: mhic461: UPSAG does not recommend this study - comments include "it can't be done" and "the answer is obvious and it is a waste of resources". It is a key FFR question however so perhaps include seed money for Pilot or RFP to see if method may exist to get done with Lidar etc. It could also be moved out in time and serve as a validation study to be done after any further rule improvements are in place.
Note on AJ71: mhic461: Money to solicit ideas for how to conduct this study via an RFP.
Note on AM24: mhic461: Aimee says these last out-year costs assume it will need to go through the ISPR process.
Note on B68: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. Uses modeling to try and determine what part of recharge areas are most influential on landslide movement.
Note on B67: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. UPSAG does not recommend this in current form. UPSAG would prefer to empirically monitor movement of active landslides where harvest occurred in groundwater recharge area.
Note on B69: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. UPSAG does not recommend pursuing this project. Expects basic science questions would not be resolved.
Note on B72: mhic461: Costs estimate would not include acquisition of LiDAR. Project a recommendation of UPSAG.
Note on AJ30: mhic461: Site acquisition costs reduced if dry and perennial done at same time.
Note on B48: mhic461: What did the first sample actually cost?
Note on AG34: mhic461: Uses default costs and assumes analysis follwed by potential case study.
Note on AJ25: mhic461: This year includes export monitoring for nutrients - which were initially elevated post harvest.
Note on B25: mhic461: Extended monitoring to look at recovery of variables increased post harvest - temperature and nutrients. Also, temperature in years 2016 and 2017 are in support of the analysis work for amphibian demographics.
Note on AG25: mhic461: Optional year for study, but it would cost to maintain monitoring network almost the same if we do not collect the data.
Note on B29: mhic461: The perennial and dry studies are matched in time to gain economies of scale and allow consideration of project integration.
Note on B54: mhic461: Can we formally ackowledge ability to use this to alternatively fill any "gaps" in knowledge? The purpose of this project is to test the effectiveness of alternative treatments which are not part of the current FFR/HCP prescription package.
Note on B50: mhic461: Not an actual project title. Currently represented in workplan at the program level by a general description that it integrates issues spanning the riparian and road rule groups.
Note on B70: mhic461: The key objective of projects developed in this program will be to understand, at a watershed scale, the cumulative effects of different sediment loads in the context of rates of management-induced versus natural landslides.
Note on AF55: mhic461: Description: The purpose of this project is to determine the development sequence of younger stands of various species compositions and densities to mature stands. The study is intended to inform management of uneven-aged stands and those of low density or mixed composition
Note on AF56: mhic461: Description: This project will evaluate the validity of the Type F performance targets and the measures of success in meeting resource objectives.
Note on AF54: mhic461: Description: The purpose of this project is to test the effectiveness of alternative treatments which are not part of the current FFR/HCP prescription package. RSAG will recommend whether to pursue this project after reviewing the results of the Westside Type F Riparian Prescription Effectiveness Project.
Note on AF71: mhic461: This project will be designed to evaluate trends in the number and volume (or area) of landslides over time at the watershed scale using landslide inventory methods similar to those of watershed analysis. In broad terms, the trend monitoring will include sites that sample statewide variability in the factors that control landslide occurrence. These sites will consist of tracts containing both FP HCP–regulated lands and other forestlands under no or less extensive management (representative of natural or background conditions). Landslide rates and volume fluxes from both will be compared. Data to infer status and trends may consist of an inventory of landslides using data collected through the Landslide Hazard Zonation Project, complemented with aerial photography, terrain, topographic, forest cover, and road network maps. When prioritized, UPSAG will work to better understand how a study might be designed to isolate the mass wasting trends associated with the forest practices rules from the dynamic noise of the natural system.
Note on AF57: mhic461: The Van Dyke’s salamander is the only one of seven Forests and Fish amphibian species that is not adequately addressed by any previous or current study. The Van Dyke’s salamander is a former Survey and Manage Species under the Northwest Forest Plan; survey protocols under the Survey and Manage Program emphasize that Van Dyke’s salamander is a stenothermic cool-adapted species and that conditions for sampling must fall under narrow moisture, relative humidity, and temperature ranges. Conflicting information exists regarding the occurrence of Van Dyke’s salamander on managed landscapes (ranging from total absence to fairly broad distribution). At least part of the disparity observed in Van Dyke’s salamander distribution across managed and unmanaged landscapes may be due to differential seasonal detectability that arises from the species’ thermal requirements. A study is being considered to address Van Dyke’s salamander distribution in three phases: (1) assemble available information to characterize current (and sometimes conflicting) information and define focal question(s); (2) develop a sampling tool, including seasonal (or thermal) sampling restrictions, that incorporates detectability estimation approaches; and (3) use that tool to identify the current distribution of Van Dyke’s salamander across the landscape.
Note on AF65: mhic461: A study design for fish passage trend monitoring was developed using guidelines consistent with the Forests and Fish Report and supplied by ISAG. The contractor (WDFW) reviewed possible monitoring approaches and presented a recommended study design and methodology that was reviewed and approved by ISAG and CMER. In addition to the WDFW study proposal, ISAG explored the potential of collecting stream crossing condition data in conjunction with the UPSAG Road Sub-Basin-Scale Effectiveness Monitoring Project. ISAG recognized that this approach would not provide all of the information needed to address the critical question but considered it a cost-effective opportunity to get supplemental information about culvert conditions from a statewide random sample. ISAG developed a set of questions for assessing culvert suitability and these questions were added to the UPSAG road survey. Status: Due to budgetary considerations and potential limitations in scope, implementation of the WDFW design has been delayed indefinitely by Policy. The UPSAG road survey was completed in 2008, and culvert conditions data were collected from approximately 1300 stream crossings. These data have not been analyzed and further investigation is pending Policy direction.

## OtherProjects
CMER Work Plan Projects Listed Below will be Prioritized and Budgeted at a Later Date by CMER/Policy.
Note: Order is not representative of review prioity. Some project may be dropped pending review of recent literature and some
projects may be added pending final results of CMER projects, further review and evaluation of "critical questions"
in CMER's Work Plan, and unforeseen needs of Policy and the Board. Projects already on Policy's "Task List" do not apply.
Type N Amphibian Response Program (Effectiveness)
Tailed Frog Literature Review
Tailed Frog meta-Analysis
Tailed Frogs and Parent Geology
DFC Validation Program (Rule Tool)
DFC Plot Width Standardization
DFC Site Class Map Validation
DFC Trajectory Model Validation
DFC Aquatic Habitat
Red Alder Growth and Yield Model
Eastside Type F Riparian Rule Tool Program
Eastside Temperature Nomograph
Eastside Type F Channel Wood Characterization
Yakima River Radiotelemetry
Westside Type F Riparian Effectiveness Program
Type F Performance Target Validation
Eastside Type F Riparian Effectiveness Program
Groundwater Conceptual Model
Hardwood Conversion Program
Annotated Bibliography Riparian Hardwood Conversion
CMZ Delineation Program
CMZ Screen and Aerial Photo Catalog and CMZ Boundary Identification Criteria
Consistency and Accuracy of CMZ Boundary Delineations
CMZ Validation Program
Projects yet to be Identified
Unstable Landform Identification Program (Rule Tool)
Shallow Rapid Landslide Screen for GIS (Eastside)
Landslide Hazard Zonation (priority 3 watersheds)
Glacial Deep-Seated Landslides Program (Rule Tool)
Evapo-Transpiration Model Refinement
Landslide Classification
Groundwater Recharge Modeling and Model Refinement
Board Manual Revision
Mass Wasting Validation Program (Intensive)
Projects yet to be identified
Roads Validation Program and Cumulative Sediment Effects
Intensive Watershed-Scale Monitoring to Assess Cumulative Effects
Fish Passage Effectiveness/Validation Monitoring Program
Projects yet to be Identified
Extensive Fish Passage Monitoring Program
Extensive Fish Passage Trend Monitoring
Forest Chemicals Program (Effectiveness)
Projects yet to be Identified
Wetlands Mapping Tools Program (Rule Tool)
DNR GIS Wetlands Data Layer
Hydrogeomorphic Wetland Classification System
Overlay Project (Wetlands Mapping)

## Sheet1
Projects almost finished |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052
Forest Practices and Wetlands Systematic Literature Review | X
Wetlands Program Research Strategy | X
Planned priority projects |  | 2015: Design; 2016: Sites; 2017: Sites&Install; 2018: Pre 1; 2019: Pre 2; 2020: Harvest; 2021: Post 1; 2022: Post 2; 2023: Analysis; 2024: CMER; 2025: ISPR
Forested Wetlands Effectiveness Study |  | 2015: 25000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
Wetland/Stream Water Temp Interactions (Add On) |  | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
Wetland Hydrologic Connectivity (Add On) |  | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
Pesticides?
Wetlands Management Zone Effectiveness Monitoring |  | 2023: 25000; 2024: 100000; 2025: 250000; 2026: 360000; 2027: 360000; 2028: 360000; 2029: 360000; 2030: 360000; 2031: 250000; 2032: 100000; 2033: 40000
Wetland/Stream Water Temp Interactions (Add On) |  | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
Wetland Hydrologic Connectivity (Add On) |  | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
|  | Pesticides? | [19 empty] | 40000 | 100000 | 250000 | 360000 | 360000 | 360000 | 360000 | 360000 | 250000 | 100000 | 40000
Wetlands Intensive Monitoring |  | 2015: Cumulative Effects/Gap fullfillment?
MP listed projects requiring more discussion with Policy
Wetlands Overlay Project | $?
Wetlands Mitigation Effectiveness (deprioitized by CMER/ Policy) | $? | 2015: Roads Study?
DNR GIS Wetlands Data Layer | $?
Hydrogeomorphic Wetland Classification System | $?
Projects from Workplan that appear still to be missing
Forest Chemicals Program (no specific projects suggested) (WetSAG Strategy ) | $? | 2015: 40000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
Note: If Pesticides is added on the forested wetlands study, seems more time will be needed for both site acquisition and harvest.
Note on A8: mhic461: Anticipate two major experimental studies with temp and connectivity as add-on costs.
Note on A18: Mark Hicks: Is this still a priority project. Perhaps it should be on the back up list. The purpose was to collect data on wetlands while doing other CMER research. With much of N work done, and no basis for integration established, this is a good idea that is too late and too undeveloped.
Note on A19: Mark Hicks: Is this still a priority project. Perhaps it should be on the back up list, or at least changed into a more generic "Road/wetlands interactions" study. It seems we determined we cannot really do an unbiased assessment of the use of the mitigation strategy. Should it be a part of the roads prescription scale study - would roads TWIG need WetSAG resources?
Note on A20: mhic461: CMER believes this is a DNR Operational task, and not a science task and should be deleted.
Note on A21: mhic461: Should be determined necessary and viable based on other planned wetland effectiveness studies. May be accomplished by these other projects. Outcome if needed would be more wetland types in the rules having different prescriptions. Should this be on list until we determine it is appropriate to regulated based on different HGM types?
Note on A25: mhic461: Addresses question of whether harvesting changes channel migration patterns.
Note on A24: mhic461: Would this likley be a stand alone study or an add on to the forested wetlands study?